## Project tasks
Project name | EMGP Automated Car
Project manager | Thomas Le
Project start date | 2022-03-26 09:00
Project finish date | 2022-04-07 10:40
Duration | 4.21 days
% complete | 34%
Exported on | 2022-04-02 02:02
Task number | Outline number | Name | Assigned to | Duration | Start | Finish | Depends on | % complete | Bucket | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items
1 | 1 | Install software XC8 1.35 |  | 40 minutes | 2022-04-01 09:00 | 2022-04-01 09:40 |  | 100% | Bucket 1 | 2 - Install software MPLAB X IDE |  |  |  | No
2 | 2 | Install software MPLAB X IDE |  | 40 minutes | 2022-04-01 09:40 | 2022-04-01 10:20 | 1 - Install software XC8 1.35 | 100% | Bucket 1 | 3 - Install software Peripherial |  |  |  | No
3 | 3 | Install software Peripherial |  | 40 minutes | 2022-04-01 10:20 | 2022-04-01 11:00 | 2 - Install software MPLAB X IDE | 100% | Bucket 1 | 4 - Inventory |  |  |  | No
4 | 4 | Inventory |  | 10 minutes | 2022-04-01 11:00 | 2022-04-01 11:10 | 3 - Install software Peripherial | 100% | Bucket 1 | 6 - Proximity Sensor, 14 - Optical Sensor, 22 - Stepped Motor, 30 - 7 Segment display, 38 - Buzzer, 5 - blinking test |  |  |  | No
5 | 5 | blinking test |  | 4 hours | 2022-04-01 11:10 | 2022-04-01 15:10 | 4 - Inventory | 100% | Bucket 1 | 6 - Proximity Sensor |  |  |  | No
6 | 6 | Proximity Sensor |  | 2.94 days | 2022-04-01 15:10 | 2022-04-06 14:40 | 4 - Inventory, 5 - blinking test | 9% |  |  | 19.5 hours | 2.5 hours | 17 hours | No
7 | 6.1 | Analysis | Cher Khor | 2 hours | 2022-04-01 15:10 | 2022-04-04 09:10 |  | 100% | Bucket 1 | 8 - component test | 2 hours | 2 hours | 0 hours | No
8 | 6.2 | component test | Cher Khor | 1 hour | 2022-04-04 09:10 | 2022-04-04 10:10 | 7 - Analysis | 50% | Bucket 1 | 9 - assignment of ports | 1 hour | 0 hours | 1 hour | No
9 | 6.3 | assignment of ports | Cher Khor | 30 minutes | 2022-04-04 10:10 | 2022-04-04 10:40 | 8 - component test | 100% | Bucket 1 | 10 - coding, 46 - Integration of all tasks assignments of ports, 12 - hardware team review | 0.5 hours | 0.5 hours | 0 hours | No
10 | 6.4 | coding | Cher Khor | 8 hours | 2022-04-04 10:40 | 2022-04-05 10:40 | 9 - assignment of ports | 50% | Bucket 1 | 11 - unit testing | 8 hours | 0 hours | 8 hours | No
11 | 6.5 | unit testing | Cher Khor | 8 hours | 2022-04-05 10:40 | 2022-04-06 10:40 | 10 - coding | 50% | Bucket 1 | 47 - Integration of all the interfaces, 13 - code review | 8 hours | 0 hours | 8 hours | No
12 | 6.6 | hardware team review |  | 4 hours | 2022-04-04 10:40 | 2022-04-04 14:40 | 9 - assignment of ports | 0% | Bucket 1 |  |  |  |  | No
13 | 6.7 | code review |  | 4 hours | 2022-04-06 10:40 | 2022-04-06 14:40 | 11 - unit testing | 0% | Bucket 1 |  |  |  |  | No
14 | 7 | Optical Sensor |  | 1.94 days | 2022-04-01 11:10 | 2022-04-05 10:40 | 4 - Inventory | 59% |  |  | 11.5 hours | 11.5 hours | 0 hours | No
15 | 7.1 | Analysis | Thomas Le | 2 hours | 2022-04-01 11:10 | 2022-04-01 13:10 |  | 100% | Bucket 1 | 16 - component test | 2 hours | 2 hours | 0 hours | No
16 | 7.2 | component test | Thomas Le | 1 hour | 2022-04-01 13:10 | 2022-04-01 14:10 | 15 - Analysis | 100% | Bucket 1 | 17 - assignment of ports | 1 hour | 1 hour | 0 hours | No
17 | 7.3 | assignment of ports | Thomas Le | 30 minutes | 2022-04-01 14:10 | 2022-04-01 14:40 | 16 - component test | 100% | Bucket 1 | 18 - coding, 46 - Integration of all tasks assignments of ports, 20 - hardware team review | 0.5 hours | 0.5 hours | 0 hours | No
18 | 7.4 | coding | Thomas Le | 4 hours | 2022-04-01 14:40 | 2022-04-04 10:40 | 17 - assignment of ports | 100% | Bucket 1 | 19 - unit testing | 4 hours | 4 hours | 0 hours | No
19 | 7.5 | unit testing | Thomas Le | 4 hours | 2022-04-04 10:40 | 2022-04-04 14:40 | 18 - coding | 100% | Bucket 1 | 47 - Integration of all the interfaces, 21 - code review | 4 hours | 4 hours | 0 hours | No
20 | 7.6 | hardware team review |  | 4 hours | 2022-04-01 14:40 | 2022-04-04 10:40 | 17 - assignment of ports | 0% | Bucket 1 |  |  |  |  | No
21 | 7.7 | code review |  | 4 hours | 2022-04-04 14:40 | 2022-04-05 10:40 | 19 - unit testing | 0% | Bucket 1 |  |  |  |  | No
22 | 8 | Stepped Motor |  | 2.94 days | 2022-04-01 11:10 | 2022-04-06 10:40 | 4 - Inventory | 9% |  |  | 19.5 hours | 2.5 hours | 17 hours | No
23 | 8.1 | Analysis | Soon Lee Teo | 2 hours | 2022-04-01 11:10 | 2022-04-01 13:10 |  | 100% | Bucket 1 | 24 - component test | 2 hours | 2 hours | 0 hours | No
24 | 8.2 | component test | Soon Lee Teo | 1 hour | 2022-04-01 13:10 | 2022-04-01 14:10 | 23 - Analysis | 0% | Bucket 1 | 25 - assignment of ports | 1 hour | 0 hours | 1 hour | No
25 | 8.3 | assignment of ports | Soon Lee Teo | 30 minutes | 2022-04-01 14:10 | 2022-04-01 14:40 | 24 - component test | 100% | Bucket 1 | 26 - coding, 46 - Integration of all tasks assignments of ports, 28 - hardware team review | 0.5 hours | 0.5 hours | 0 hours | No
26 | 8.4 | coding | Soon Lee Teo | 8 hours | 2022-04-01 14:40 | 2022-04-04 14:40 | 25 - assignment of ports | 0% | Bucket 1 | 27 - unit testing | 8 hours | 0 hours | 8 hours | No
27 | 8.5 | unit testing | Soon Lee Teo | 8 hours | 2022-04-04 14:40 | 2022-04-05 14:40 | 26 - coding | 0% | Bucket 1 | 47 - Integration of all the interfaces, 29 - code review | 8 hours | 0 hours | 8 hours | No
28 | 8.6 | hardware team review |  | 4 hours | 2022-04-01 14:40 | 2022-04-04 10:40 | 25 - assignment of ports | 0% | Bucket 1 |  |  |  |  | No
29 | 8.7 | code review |  | 4 hours | 2022-04-05 14:40 | 2022-04-06 10:40 | 27 - unit testing | 0% | Bucket 1 |  |  |  |  | No
30 | 9 | 7 Segment display |  | 1.81 days | 2022-04-01 11:10 | 2022-04-05 09:40 | 4 - Inventory | 57% |  |  | 10.5 hours | 10.5 hours | 0 hours | No
31 | 9.1 | Analysis | Lily Zhang | 1 hour | 2022-04-01 11:10 | 2022-04-01 12:10 |  | 100% | Bucket 1 | 32 - component test | 1 hour | 1 hour | 0 hours | No
32 | 9.2 | component test | Lily Zhang | 1 hour | 2022-04-01 12:10 | 2022-04-01 13:10 | 31 - Analysis | 100% | Bucket 1 | 33 - assignment of ports | 1 hour | 1 hour | 0 hours | No
33 | 9.3 | assignment of ports | Lily Zhang | 30 minutes | 2022-04-01 13:10 | 2022-04-01 13:40 | 32 - component test | 100% | Bucket 1 | 34 - coding, 46 - Integration of all tasks assignments of ports, 36 - hardware team review | 0.5 hours | 0.5 hours | 0 hours | No
34 | 9.4 | coding | Lily Zhang | 4 hours | 2022-04-01 13:40 | 2022-04-04 09:40 | 33 - assignment of ports | 100% | Bucket 1 | 35 - unit testing | 4 hours | 4 hours | 0 hours | No
35 | 9.5 | unit testing | Lily Zhang | 4 hours | 2022-04-04 09:40 | 2022-04-04 13:40 | 34 - coding | 100% | Bucket 1 | 47 - Integration of all the interfaces, 37 - code review | 4 hours | 4 hours | 0 hours | No
36 | 9.6 | hardware team review |  | 4 hours | 2022-04-01 13:40 | 2022-04-04 09:40 | 33 - assignment of ports | 0% | Bucket 1 |  |  |  |  | No
37 | 9.7 | code review |  | 4 hours | 2022-04-04 13:40 | 2022-04-05 09:40 | 35 - unit testing | 0% | Bucket 1 |  |  |  |  | No
38 | 10 | Buzzer |  | 1.81 days | 2022-04-01 11:10 | 2022-04-05 09:40 | 4 - Inventory | 57% |  |  | 10.5 hours | 10.5 hours | 0 hours | No
39 | 10.1 | Analysis | Lily Zhang | 1 hour | 2022-04-01 11:10 | 2022-04-01 12:10 |  | 100% | Bucket 1 | 40 - component test | 1 hour | 1 hour | 0 hours | No
40 | 10.2 | component test | Lily Zhang | 1 hour | 2022-04-01 12:10 | 2022-04-01 13:10 | 39 - Analysis | 100% | Bucket 1 | 41 - assignment of ports | 1 hour | 1 hour | 0 hours | No
41 | 10.3 | assignment of ports | Lily Zhang | 30 minutes | 2022-04-01 13:10 | 2022-04-01 13:40 | 40 - component test | 100% | Bucket 1 | 42 - coding, 46 - Integration of all tasks assignments of ports, 44 - hardware team review | 0.5 hours | 0.5 hours | 0 hours | No
42 | 10.4 | coding | Lily Zhang | 4 hours | 2022-04-01 13:40 | 2022-04-04 09:40 | 41 - assignment of ports | 100% | Bucket 1 | 43 - unit testing | 4 hours | 4 hours | 0 hours | No
43 | 10.5 | unit testing | Lily Zhang | 4 hours | 2022-04-04 09:40 | 2022-04-04 13:40 | 42 - coding | 100% | Bucket 1 | 47 - Integration of all the interfaces, 45 - code review | 4 hours | 4 hours | 0 hours | No
44 | 10.6 | hardware team review |  | 4 hours | 2022-04-01 13:40 | 2022-04-04 09:40 | 41 - assignment of ports | 0% | Bucket 1 |  |  |  |  | No
45 | 10.7 | code review |  | 4 hours | 2022-04-04 13:40 | 2022-04-05 09:40 | 43 - unit testing | 0% | Bucket 1 |  |  |  |  | No
46 | 11 | Integration of all tasks assignments of ports | Cher Khor | 2 hours | 2022-04-04 10:40 | 2022-04-04 12:40 | 33 - assignment of ports, 25 - assignment of ports, 41 - assignment of ports, 17 - assignment of ports, 9 - assignment of ports | 0% | Bucket 1 |  | 2 hours | 0 hours | 2 hours | No
47 | 12 | Integration of all the interfaces | Thomas Le | 8 hours | 2022-04-06 10:40 | 2022-04-07 10:40 | 43 - unit testing, 35 - unit testing, 27 - unit testing, 19 - unit testing, 11 - unit testing | 0% | Bucket 1 |  | 8 hours | 0 hours | 8 hours | No